## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Rakesh Babu Gajula | 2026-08-20 | Initial semantic retrieval returned weakly related defects for some queries. | 2026-08-21 | Rakesh Babu Gajula | Logical | Created balanced multi-source dataset and validated retrieval. | 2026-08-21 | Closed | Resolved by improving balanced dataset construction and validating semantic retrieval quality.
2 | Rakesh Babu Gajula | 2026-08-21 | Mozilla had significantly fewer records than Apache and Eclipse in the unified dataset. | 2026-08-22 | Rakesh Babu Gajula | Logical | Created balanced test dataset with 2,000 Apache, 2,000 Eclipse and 99 Mozilla records. | 2026-08-22 | Closed | Resolved by balancing Apache, Eclipse and Mozilla records for representative retrieval.
3 | Rakesh Babu Gajula | 2026-08-22 | Missing technical logs resulted in insufficient evidence for precise root-cause analysis. | 2026-08-23 | Rakesh Babu Gajula | Logical | Added separate no-log and stack-trace analysis tests. | 2026-08-23 | Closed | Resolved by adding dedicated no-log and stack-trace analysis test scenarios.
4 | Rakesh Babu Gajula | 2026-08-23 | Semantic similarity alone could not establish duplicate status. | 2026-08-24 | Rakesh Babu Gajula | Logical | Added evidence/conflict analysis in Duplicate Detection Agent. | 2026-08-24 | Closed | Resolved by combining semantic similarity with multi-attribute evidence and conflict analysis.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others